## Improvements_Case
Project Name | Nurul Quran
Leads | Iffat Sister
Scope Of Documents | To Analyze the website as per the users view for any improvements
Date | 2018-12-13
Version | Base Version 1
Create By | Ayesha Murshid Khan
Srno | Screen | Sub Screen Part | Link / Path / Navigation | Changes Required | Category | Severity | Additional Comments | Refrence Screenshot
1 | HomePage | Homepage Header | https://nurulquran.com/ | There is an empty space between Logo and Search. Need to add Tag line or Meaning like “Enlighten Your Lives with the Nurul of Al Quran” | User Interface Changes | Medium |  | MainScreen Header.png
2 | HomePage | Homepage Header | https://nurulquran.com/ | Search : It should be Suggestive search. For instance google search | Additional Features | Medium | Why do we required two home bottom | SuggestiveSerach.png
3 | HomePage | Homepage Header | https://nurulquran.com/ | Two Home icon in the main Screen : 1) First one is logo 2)Menu Bar | User Interface Changes | Medium |  | Ytwohome
4 | HomePage | Homepage Footer | https://nurulquran.com/ | Contact details .For Eg : Tried to contact on India's Contact Number but was unavailable .Decision shloud be taken by Head of Nurul Quran for Contact number to be display or not | Based on requirement | High | Personally , was trying to get some information was not able to reach . | HomePageFooter.png
5 | AboutUS | About NurulQuran | https://nurulquran.com/about-nurulquran/ | Content is fine . Suggestion is that appreance shloud be more attractive. | Display Changes | Low
6 | AboutUS | About Instructor | https://nurulquran.com/about-instructor/ | Content is fine . Suggestion is that appreance shloud be more attractive. | Display Changes | Low
7 | Video | Video Menu | https://nurulquran.com/video/ | 1) Page should be displayed in the main screen (Home Page )ie Web Page Body : ( Separate Page should not be display ) for Video | Based on requirement | High | Don’t know about the Constraint . Why its kept separate page | VideoMenuBar.png
8 | Video | Video Menu | https://nurulquran.com/video/ | 2)All Menu in the Menu Bar shloud be dropdown list on Main screen in Video tab. Like About US | Based on requirement | High
9 | General Layout | NA | NA | This is for all the screen . Menu bar , header and footer of all screen shloud be in sync | Suggestion | Medium
10 | Course | Course Menu | https://nurulquran.com/courses/ | All the course details have been given in the Picture format . Their should be PDF download opition for the course | Suggestion | Medium | Didn’t understand the concept of showing all the on going course .1)Anybody can join the Course from between and can register for it 2) It should be displayed as Upcoming Course ,Ongoing Course and Completed as a sub Menu inside Course
11 | Event | Event | https://nurulquran.com/events/ | All the other menus , Sub Menu get enable . This is an issue with code | Code Issue | High |  | EventMenu.PNG
12 | Event | SerachEvent | https://nurulquran.com/events/month/?tribe-bar-date=2018-12&tribe-bar-search=asds | Giving the input for serach event . If no event found for the combination of input giving while searching the event, Than no table should be displayed | Code Issue | High |  | Tablecontent shld not display anuthign.PNG
13 | Event | Event | https://nurulquran.com/events/ | Table content for the Event is too big . | Display Changes | Low |  | Table content and cell to big.PNG
14 | Student's Corner | Blogs | https://nurulquran.com/blogs/ | Display of the blogs are confusing . It should have proper spacing between the blogs ,For example Surah Hud notes . Below it image text is present | Display Changes | Medium |  | ConfusingwithblogDisplay.PNG
15 | General Issue | All Screen |  | All the Sub Menu get Enable when someone try to decreased the size of the page | Code Issue | High | Its code issue . Need to debug the code and check why is control of Sub Menu get display .
16 | Student's Corner | Activites | https://nurulquran.com/wp-content/uploads/2018/02/MyGoals-1.jpg | Its showing error 404 . | Code Issue | High | Advice : Before Going live do check .ie testing | Activity_MyGoal.png
17 | Student's Corner | Activites | https://nurulquran.com/wp-content/uploads/2018/02/MyGoals-1.jpg | Also no Back button or Link | Code Issue | Medium |  | Activity_MyGoal.png
18 | Student's Corner | Activites | https://nurulquran.com/wp-content/uploads/2018/02/ChangeOfQibla.pdf | PDF or any download should open in another tab or window | Suggestion | Low
19 | Student's Corner | Activites | https://nurulquran.com/wp-content/uploads/2018/02/AyatEDain.pdf | Its showing error 404 . | Code Issue | High | Advice : Before Going live do check .ie testing
20 | Student's Corner | Activites | https://nurulquran.com/qualities-that-allah-swt-loves/ | Its showing error 404 . And also refer the path in link column is showing different path compared to other activites . It shld be in same folder | Code Issue | High | Advice : Before Going live do check .ie testing
21 | Student's Corner | Activites | https://nurulquran.com/hajj/ | As it said earlier that all the PDF or Document or Reading Material . Downloads show open in new tab . | Design Change | MEdium |  | Activity_Hajj.PNG
22 | Student's Corner | Activites | https://nurulquran.com/hajj/ | With Reference to Hajj Activity . It Show same error of Sub Menu . | Code Issue | High |  | Activity_Hajj.PNG
23 | Student's Corner | Activites | https://nurulquran.com/hajj/ | The path of all the data or Document should be under same path . Kindly refer the link | Code Issue | Medium
24 | Student's Corner | Activites | https://nurulquran.com/3-secrets-of-success/ | 1)Path in the link is different 2) 404 error display | Code Issue | Medium |  | Activity_3-secrets-of-success.PNG
25 | Student's Corner | Activites | https://nurulquran.com/my-life-changes/ | 1)Path in the link is different 2) 404 error display | Code Issue | Medium |  | Activity_MyLifeChange.PNG
26 | Student's Corner | Activites | https://nurulquran.com/dos-and-donts-in-surah-albaqara/ | 1)Path in the link is different 2) 404 error display | Code Issue | Medium
27 | Student's Corner | Activites | https://nurulquran.com/islamic-belief/ | 1)Path in the link is different 2) 404 error display | Code Issue | Medium
28 | Student's Corner | Activites | https://nurulquran.com/islam-a-z/ | Path of the Doc in the link is different | Code Issue | Low
29 | Student's Corner | Activites | https://nurulquran.com/wp-content/uploads/2018/02/Sharing.mp3 | Path of the Doc in the link is different | Code Issue | Low
30 | Student's Corner | Testimonial | https://nurulquran.com/testimonial/ | NurulQuran Students Sharing part some of the Caption Details is "". Kindly mention name on its | Code Issue | Low |  | Testimonial_CapitionMissing.PNG
31 | Other Resources | WhatsApp | https://nurulquran.com/whatsapp/ | Case: 1. Was Able to submit the form with junk data 2. Also was able to submit the same data in the form. Suggestion: Need to handle all this cases. Basic Validation required | Code Issue | Medium |  | NQWhatsAppEnglish.PNG
32 |  | UseFul Websites | https://nurulquran.com/useful-websites/ | Minor Changes : Content is Fine but there is spacing issue with Hyper link and links . Kindly keep space between word and links | Code Issue | Low |  | UseFul_WebsitesDetails.PNG
33 | Earn Rewards | Refer a Friends | https://nurulquran.com/refer/ | Only the content is displayed . Can put some Images? | Suggestion | Low
34 | Contact US | General Queries | https://nurulquran.com/general-contact-us/ | Like Refer a Friends Tab . Their should be more information on General Queries | Suggestion | Low
35 | Contact US | Subscribe Us | https://nurulquran.com/subscribe-us/ | Nothing displayed in Body of the Page | Suggestion | Low